## Main
Project Inputs | Values | Calculated Metrics | Results
Budget at Completion (BAC) | 60000 | Planned Value (PV) | 15000
Planned Percent Complete (%) | 25% | Earned Value (EV) | 16800
Actual Percent Complete (%) | 28% | Cost Variance (CV) | -1200
Actual Cost (AC) | 18000 | Schedule Variance (SV) | 1800
|  | Cost Performance Index (CPI) | 0.93333
|  | Schedule Performance Index (SPI) | 1.12
|  | Estimate at Completion (EAC) | 64285.7143
|  | Estimate to Completion (ETC) | 46285.7143
*Cells C3 through C6 are all input cells, whose |  | Variance at Completion (VAC) | -4285.7143
input values will determine the calculated outputs. |  | To-Complete Performance Index (TCPI) | 1.0286

## PERT
Category | Value | Calculated Metrics | Results
Optimistic Estimate | 8 | Optimistic (O) | 8
Most-Likely Estimate | 9 | Most-Likely (M) | 36
Pessimistic Estimate | 11 | Pessimistic (P) | 11
Denominator | 6 | Total (Numerator) | 55
|  | Quotient | 9.1667
|  | PERT Estimate | 9.1667
*Cells C3 through C6 are all input cells, whose
input values will determine the calculated outputs.

## Main (v1)
Project Inputs | Values | Calculated Metrics | Results
Budget at Completion (BAC) | 60000 | Planned Value (PV) | 15000
Planned Percent Complete (%) | 25% | Earned Value (EV) | 16800
Actual Percent Complete (%) | 28% | Cost Variance (CV) | -1200
Actual Cost (AC) | 18000 | Schedule Variance (SV) | 1800
|  | Cost Performance Index (CPI) | 0.93333
|  | Schedule Performance Index (SPI) | 1.12
|  | Estimate at Completion (EAC) | 64285.7143
|  | Estimate to Completion (ETC) | 46285.7143
*Cells C3 through C6 are all input cells, whose |  | Variance at Completion (VAC) | -4285.7143
input values will determine the calculated outputs. |  | To-Complete Performance Index (TCPI) | 1.0286

## PERT (v1)
Category | Value | Calculated Metrics | Results
Optimistic Estimate | 8 | Optimistic (O) | 8
Most-Likely Estimate | 9 | Most-Likely (M) | 36
Pessimistic Estimate | 11 | Pessimistic (P) | 11
Denominator | 6 | Total (Numerator) | 55
|  | Quotient | 9.1667
|  | PERT Estimate | 9.1667
*Cells C3 through C6 are all input cells, whose
input values will determine the calculated outputs.

## Information
PROJECT INPUTS | Values | CALCULATED METRICS | Results
Budget at Completion (BAC) | Enter your budget here | Planned Value (PV) | #VALUE!
Planned % Complete | Enter planned progress as a % | Earned Value (EV) | #VALUE!
Actual % Complete | Enter actual progress as a % | Cost Variance (CV) | #VALUE!
Actual Cost (AC) | Enter costs to date here | Schedule Variance (SV) | 0
|  | Cost Performance Index (CPI) | #VALUE!
|  | Schedule Perf. Index (SPI) | #VALUE!
|  | Estimate at Completion (EAC) | #VALUE!
|  | Estimate to Completion (ETC) | #VALUE!
|  | Variance at Completion (VAC) | #VALUE!
|  | To-Complete Perf. Index (TCPI) | #VALUE!